AI Technical Program Manager — UST

Week 1 · Participant Workbook

Your working file for Days 2 and 3. Fill it in as you go, then submit this same file.

For: every participant. Save your own copy before you start typing.

File name for your copy: UST_AITPM_Week1_Workbook_208798

Used in: Day 2 (M1 and M2) and Day 3 (M3 and M4). Instructions, hints and examples are in the Lab Kit; this file holds only the forms.

# Before you begin: why this document exists

### Why this step is needed

Your Week 1 work is scored by an evaluation agent that reads your submission and must quote your own words for every score. If your findings, owners, checklist and readiness statement are spread across several files, or written in a format the evaluator cannot read, you lose marks you have earned. One workbook keeps everything in one place, in the right order.

### What exactly happens in this step

You fill in six parts over the two lab sessions: the cover block, the Findings Log (M1, Day 2), the governance frame (M2, Day 2), Release-Readiness Checklist v1 (M3, Day 3), the readiness statement to the sponsor and your assumptions (M4, Day 3). At the end of Day 3 you check it and submit this file.

### The purpose of what is being done

To let you spend the lab thinking instead of formatting, and to make sure the evaluator finds every piece of evidence for your score exactly where it expects it.

### Which part of the programme architecture this builds

This is the submission file for Week 1, whose work product is Release-Readiness Checklist v1. The same structure (findings, frame, checklist, statement) is reused in later weeks, and your Checklist v1 becomes the first layer of your Week 6 capstone.

# How to use this workbook

| Do | Do not |
| --- | --- |
| Type directly into the tables. Add rows wherever you need them (in Word: right-click a row, then Insert). | Paste screenshots, images or diagrams instead of text. The evaluator can only score words it can quote. |
| Delete the grey example rows before you submit. | Write "TBD", a team name, or a role without a person where an owner is asked for. |
| Use only the people in the Scenario Pack org chart (Part A3). | Invent people, numbers or documents that the case does not contain. If you must assume something, record it in Part 6. |
| Save often, and keep a copy somewhere you can open tomorrow. | Polish the formatting. Polish earns nothing; specific, checkable content earns everything. |

# Part 1 · Cover block

| Field | Your entry |
| --- | --- |
| Candidate id | [your candidate id] |
| Week | Week 1 · Exercise 2 · Release-Readiness Checklist v1 (Kestrel / Beacon) |
| Domain track used | Healthcare (Kestrel Health Network) |
| Did you use your own live project instead of the case? | No |
| AI tool(s) used | Claude (Anthropic) |
| Day 2 partner (M1 and M2) | None: Exercise 2 is an individual exercise |
| Day 3 peer reviewer (M4) | None: Exercise 2 is an individual exercise |
| Attempt number | 1 |
| Date submitted | 30/10/2026 |

# Part 2 · Findings Log (M1, Day 2)

Record every weakness in checklist v0.9 that would stop a careful stranger trusting that Beacon is ready. Aim for 12 to 20 findings, with at least one for each of the five dimensions. See the Lab Kit, Section 2.

Category: use one or more of Dimension gap · Ownership · AI control · Stage gate · Evidence · Contradiction. Evidence reference: the Scenario Pack part and item, for example "Part C1, report footer" or "Part C2, 4 Nov message".

| # | v0.9 item(s) | Finding (what is wrong) | Category | Why it matters (for the sponsor) | Evidence reference | What v1 must contain instead |
| --- | --- | --- | --- | --- | --- | --- |
| F1 (Critical) | 10; appendix threshold note | Item 10 says the threshold is 0.80 per ev-118, but the live config is 0.72. Imran lowered it on 25 Nov to shrink the nurse queue, with no re-evaluation and no CSO approval. The appendix also lets Engineering tune it. | AI control; Contradiction; Evidence | More messages are auto-routed or auto-answered at a threshold nobody has tested. This breaks AIP-2, so a patient could be harmed under an unapproved setting. | Part B item 10 and appendix; Part C E3 (auto_route_threshold: 0.72); E4 (26 Nov); Part A4 AIP-2 | AI-01 row: metric, number, source data, named owner, below-threshold action; any change re-evaluated on Kestrel data and approved by the CSO before use |
| F2 (Critical) | 11 | The 'clinical safety case signed' is Corvid's hazard log v2, signed by Corvid's CSO and owned by Neha. It has no hazards for automated replies, mixed-language messages or nurse queue capacity. Kestrel's CSO has not been asked to review it. | Ownership; Evidence; Contradiction | CSS-1 requires a Kestrel safety case owned and signed by Kestrel's CSO. Without it, Beacon cannot lawfully influence patient care. | Part B item 11; Part C E7, E2; Part A4 CSS-1 | Kestrel clinical safety case and hazard log, covering Beacon's real use, signed by Dr. Helen Mathews |
| F3 (Critical) | 18 | Risk R-17 (mixed-language under-triage 6.8% vs 1.6% for English) was 'accepted' by Neha Sharma on behalf of delivery 'so we stay green'. No review date. Owen recorded it as accepted. | Ownership; AI control; Contradiction | Under AIP-2 only the CMO or CSO can accept a clinical risk, in writing, with a review date. Patients writing in Hindi or Marathi mix are four times as likely to be under-triaged. | Part C E1 (under-triage rows); E4 (5 Dec, 7 Dec); Part B item 18; Part A4 AIP-2 | R-17 either mitigated (all mixed-language messages to nurses) or accepted in writing by Dr. Anjali Rao or Dr. Helen Mathews with a review date |
| F4 (Critical) | 9, 27; config model alias | Beacon calls the floating alias 'corvid-med-latest'. Corvid will move it to corvid-med-3.3 on 15 Dec, the day after pilot go-live, calling it 'non-material'. Item 27 says a change process is agreed, but the contract only gives notice. | AI control; Contradiction; Evidence | The model would change under live patients one day into the pilot, without the re-evaluation and CSO approval AIP-2 requires. A supplier's 'non-material' label is a claim, not evidence. | Part C E3 (model: corvid-med-latest); E4 (30 Nov notice); E8 item 27 (CTR-311 clause 9.4) | Model version pinned; any model change re-evaluated on Kestrel data and approved by the CSO before use |
| F5 (Critical) | 8, 9, 10 | Item 9 'model validated (96%)' is Corvid's benchmark on US and UK messages. The only Kestrel evaluation (ev-118) ran on build 1.4.0 at 0.80, not on build 1.4.2 at 0.72. The regression suite does not include the evaluation set. Items 8 and 9 are owned by Jonas Weber, who left on 16 Oct. | Evidence; Stage gate; Ownership | There is no evidence that the build and settings going live are safe for Kestrel patients, and nobody is accountable for the claim. | Part C E1 footer; E2; E4 (27 Nov, Victor Osei); Part A3 (Jonas Weber left) | Kestrel evaluation on the exact release build, pinned model and configured threshold, owned by a current named person |
| F6 (Critical) | 19, 20 | The 'Beacon Drift' dashboard compares against CorvidBench, not Kestrel data. It has no under-triage measure, and no clinician sampling is scheduled. Alerts go to a 14-member chat channel that is not on any on-call rota. | AI control; Ownership; Evidence | The most dangerous failure, urgent patients routed as routine, would not be detected, and no one would be called if it were. | Part C E5; Part B items 19, 20 | AI-03 row: under-triage from clinician sampling, Kestrel baseline, band, paged alert, named responder, switch-to-manual action |
| F7 (Critical) | 17 | Item 17 promises a 30-minute response for urgent cases. Two night nurses, who also cover the ward phone line, need about 75 minutes to clear the 7 to 10 pm urgent peak. | AI control; Contradiction | Urgent patients would wait more than twice the promised time on the busiest nights. | Part B item 17; Part C E4 (1 Dec, Priyanka Das) | AI-02 row with trigger, receiving role and time limit, backed by a staffing check against the peak |
| F8 (Critical) | 25, 17 | When a patient replies to a self-care message to say 'it's getting worse', the reply goes to the general inbox, answered within 48 hours. The contact centre got only an email link: no scripts, no escalation route. | AI control; Dimension gap (Operational); Evidence | A deteriorating patient could wait two days for a response to a warning sign. | Part C E4 (3 Dec, Sunil Bhat); E8 item 25 | Any reply to an automated message routed to the nurse queue as a human-review trigger; contact-centre scripts and escalation route |
| F9 (Critical) | 14 | DPIA v1 (August) covers referral letters only. Portal messages were added on 9 Oct and the DPO says an addendum is needed before patient messages are processed. Item 14 is ticked. | Evidence; Contradiction | Processing patients' own messages without an approved DPIA is a data protection breach. | Part B item 14; Part C E4 (2 Dec, Grace Liu) | DPIA addendum for portal messages approved by Grace Liu before any patient message is processed |
| F10 (Critical) | 22 | Retention is 365 days. RP-1 requires 8 years for patient communications and care decisions. The owner is 'Platform / Nursing (joint)'. | Contradiction; Ownership | Triage decisions and automated replies would be deleted seven years early, and two teams 'own' the setting, so no one does. | Part B item 22; Part C E3 (retention_days: 365); Part A4 RP-1 | Retention of 8 years verified in configuration, owned by one named person |
| F11 (Critical) | 21 | Audit logging records only message_id, category and confidence. It does not record the rationale, model version, prompt version, threshold, routing outcome, reply text or reviewing nurse. | Evidence; AI control | Kestrel could not reconstruct why a patient was triaged as they were, or what they were told. | Part B item 21; Part C E3 (log_fields) | Decision-level audit record with all of these fields, kept for 8 years |
| F12 (Critical) | 26, 16 | Self-care replies read at grade 11 (standard: grade 8), are in English only, and the AI disclosure wording is still a draft with Legal. Item 26 is ticked. Item 16 marks accessibility N/A as a 'backend service', though Beacon writes to patients. | Contradiction; Evidence; Dimension gap | Every automated reply would breach PCS-3: too hard to read, not in Hindi or Marathi, and without approved disclosure. | Part C E1 (reading level); E8 item 26; Part B items 16, 26; Part A4 PCS-3 | Reply readability at grade 8 or below, in the patient's chosen language, with approved AI disclosure |
| F13 (High) | 30; appendix stage-gate approvals | All five stage gates were approved by Neha Sharma on the same day (2 Dec), and she wrote the checklist. The Go/No-Go is called 'a formality'. | Stage gate; Ownership | The delivery lead marked her own work. No independent person has checked any gate. | Part B appendix; item 30 | Each gate approved by an independent named approver, with the artefact they checked |
| F14 (High) | 3; Intent stage | intent.md covers referral letters only. Portal messages and automated replies were added by a team-channel decision on 9 Oct. Item 3 'scope confirmed' relies on spec v3. | Stage gate; Evidence | The highest-risk scope (patients' own messages and automated replies) was never agreed at the intent stage. | Part A5 Intent row; Part B item 3 | Updated intent.md approved by the business owner, covering portal messages and automated replies |
| F15 (High) | 3, 11; Spec stage | spec.md v3's clinical safety section is copied from Corvid's hazard log, written by a coding agent and approved by Neha. | Stage gate; Evidence | The spec gives Kestrel no safety requirements of its own for the features it added. | Part A5 Spec row | Spec clinical safety section derived from the Kestrel hazard log and approved by the CSO |
| F16 (High) | 6 | Item 6 says plans are complete, but 'automated reply drafting' and 'threshold tuning' have no plan; they were called 'small config features'. | Stage gate; Contradiction | The two features that most affect patient safety were built without an approved plan. | Part A5 Plan row; Part B item 6 | Approved plans for every feature, including these two |
| F17 (High) | 23 | Rollback was rehearsed only for the application container. The runbook does not cover the model version, prompt version, or switching Beacon off so all messages go to nurses. | Evidence; AI control | If the model starts mis-triaging, there is no tested way to stop it. | Part C E6; Part B item 23 | Rollback covering container, model and prompt version, plus a rehearsed switch to manual triage |
| F18 (High) | 12 | Item 12 says 87 of 87 PRs were approved, but 12 were approved by Imran, who wrote the prompts the coding agent used to produce them. About 70% of PRs were agent-written. | Stage gate; Ownership | Those changes had no independent human review. | Part A5 Review row; Part B item 12 | Rule that no PR is approved by its author or by the author of its prompts; the 12 PRs re-reviewed |
| F19 (High) | 4, 15, 23; appendix ownership note | Architecture review ADR-009 (21 Sep) predates the 9 Oct scope change. Tobias Grant owns technical items 'until handover', but his contract ends on 18 Dec, before the network rollout. | Ownership; Stage gate; Evidence | The architecture was never reviewed for the current scope, and the technical owner leaves mid-rollout with no handover. | Part C E8 item 4; Part A3 (Tobias Grant); Part B appendix | Architecture re-review of current scope; technical accountability with a Kestrel employee and a dated handover |
| F20 (High) | 24 | Item 24 'nurses trained' is ticked because the module was assigned. Only 11 of 29 pilot-site nurses (38%) have completed it. | Contradiction; Evidence | Most nurses receiving Beacon cases have not been trained to use it. | Part C E8 item 24 | Training completed by all pilot-site triage nurses before go-live |
| F21 (High) | 8, 9 | Items 8 and 9 are owned by Jonas Weber, who left Kestrel on 16 Oct. Victor Osei has owned the test strategy since November. | Ownership | Nobody currently at Kestrel answers for these claims. | Part A3 (Jonas Weber, Victor Osei) | Every row owned by a current employee |
| F22 (Medium) | 28; appendix rollout note | The appendix says the network rollout 'proceeds per Rollout plan v2' once the pilot Go/No-Go passes. There is no separate network gate. | Stage gate; Dimension gap | Nine hospitals would go live on 11 Jan without anyone checking the pilot's results. | Part B item 28 and appendix | A network phase gate before 11 Jan, using pilot evidence |
| F23 (Medium) | 15 | The load test passed at 3x pilot volume (p95 1.8 s), but it says nothing about nine-hospital volume, and its owner is the departing architect. | Evidence; Ownership | Valid for the pilot, but not for the network rollout. | Part B item 15; Part A3 (Tobias Grant) | Pilot load test kept as met; separate network-volume test owned by Victor Osei |
| F24 (Medium) | 1 | The business case (August) was approved for referral letters only. It has no measures for the expanded scope or for pilot benefits, such as nurse queue and response time. | Dimension gap; Evidence | The sponsor cannot tell whether the pilot delivered benefits before the network decision. | Part B item 1; Part A5 Intent row | Benefit measures for the current scope, with baselines, reviewed at the network gate |
| F25 (Low) | 22; appendix ownership note | Operational ownership is 'joint between Platform and Nursing'. | Ownership | Joint ownership means no single person is accountable. | Part B appendix | One accountable owner per row |
| F26 (Low) | 29 | Item 29 (board communication) is ticked because the pilot is in the annual report, and Marcus says it 'cannot slip'. | Evidence | A public announcement is pressure, not evidence of readiness. | Part B item 29; Part C E4 (4 Dec) | Remove from readiness criteria; report to the board on the gate decision instead |

Delete the grey F0 example row before you submit. It comes from Project Harbour (Day 1), not from your case.

# Part 3 · Governance frame (M2, Day 2)

Decide the structure of your checklist before you write it. See the Lab Kit, Section 3.

## 3a. Who owns each dimension?

Exactly one Accountable person per dimension, by name, from the org chart. One person may own two dimensions; one dimension never has two Accountables. Test each with the Saturday question: if this fails on go-live weekend, is this the person whose phone rings?

| Dimension | Accountable (one named person) | Responsible | Consulted | Informed | Why this person (one sentence) |
| --- | --- | --- | --- | --- | --- |
| Business | Marcus Bell | Neha Sharma | Dr. Anjali Rao; Priyanka Das | Sunil Bhat | He owns the business case, budget and model contract, so he decides whether the expanded scope and pinned model are funded. |
| Technical | Neha Sharma | Imran Qureshi; Tobias Grant (until 18 Dec) | Rahul Menon; Kavya Nair | Victor Osei | She runs delivery and stays with Kestrel; Tobias leaves on 18 Dec, so he cannot be accountable through 11 Jan. |
| Quality | Victor Osei | Dr. Farah Siddiqui | Dr. Helen Mathews | Neha Sharma | He has owned the test strategy since November and replaces Jonas Weber, who has left. |
| Governance | Dr. Helen Mathews | Owen Fletcher; Grace Liu | Rahul Menon | Dr. Anjali Rao | As CSO she owns CSS-1 and is one of only two people AIP-2 allows to accept clinical risk. |
| Operational | Kavya Nair | Priyanka Das; Sunil Bhat | Dr. Helen Mathews | Neha Sharma | She owns monitoring, alerting, rollback and the on-call rota, which are the controls that act when Beacon goes wrong. |

## 3b. Where is each dimension checked? (stage-gate map)

In each cell where a gate exists, write who approves crossing it and the artefact they look at, for example "Approver: name · Artefact: signed eval report". Leave the cell empty where there is no gate. Use all six stages; at least three dimensions should have gates at more than one stage.

| Dimension | Intent | Spec | Plan | Build | Review | Deploy |
| --- | --- | --- | --- | --- | --- | --- |
| Business | Approver: Marcus Bell · Artefact: updated intent.md covering portal messages and automated replies (pilot) |  | Approver: Marcus Bell · Artefact: signed pinned-model contract change (pilot) |  |  | Approver: Dr. Anjali Rao · Artefact: pilot Go/No-Go pack (pilot); pilot benefit and safety report (network) |
| Technical |  | Approver: Rahul Menon · Artefact: architecture re-review of current scope (pilot) | Approver: Neha Sharma · Artefact: approved plans for all 11 features (pilot) | Approver: Neha Sharma · Artefact: config showing pinned model and full log fields (pilot) | Approver: Victor Osei · Artefact: re-review of the 12 self-approved PRs (pilot) | Approver: Priyanka Das · Artefact: rehearsed switch-to-manual rollback (pilot); Marcus Bell · technical handover record (network) |
| Quality |  |  |  | Approver: Dr. Helen Mathews · Artefact: Kestrel evaluation on build 1.4.2, pinned model, configured threshold (pilot) | Approver: Dr. Helen Mathews · Artefact: reply readability and language review (network) | Approver: Kavya Nair · Artefact: load test at nine-hospital volume (network) |
| Governance |  | Approver: Dr. Helen Mathews · Artefact: spec safety section from Kestrel hazard log (pilot) |  |  | Approver: Dr. Anjali Rao · Artefact: Kestrel safety case signed by CSO (pilot); Owen Fletcher · DPIA addendum (pilot) | Approver: Dr. Helen Mathews · Artefact: R-17 closure or written acceptance with review date (network) |
| Operational |  |  | Approver: Dr. Anjali Rao · Artefact: night-shift staffing plan for urgent peak (pilot) |  |  | Approver: Dr. Helen Mathews · Artefact: paged under-triage alert test (pilot); Dr. Anjali Rao · pilot operations review (network) |

3c. What is the 10 December Go/No-Go meeting for now? (one sentence) To confirm, from linked evidence, that the pilot gates listed in Part 4 have already been passed by their named approvers, and to record Dr. Anjali Rao's go, no-go or conditional decision for 14 December; it is not where gaps are found. Pilot gate (by 14 Dec): Kestrel safety case signed by the CSO; model pinned; threshold re-evaluated or reset to the evaluated 0.80; DPIA addendum approved; 8-year retention and full decision logging; tested switch to manual triage; nurse staffing and training in place. Network gate (by 11 Jan): pilot under-triage sample within band; R-17 closed or accepted by CMO or CSO; replies at grade 8 in English, Hindi and Marathi with disclosure; paged drift alerts live; network load test; technical handover from Tobias Grant.

# Part 4 · Release-Readiness Checklist v1 (M3, Day 3)

This is the scored work product. Write 20 to 35 rows. Every row needs all nine columns filled. See the Lab Kit, Sections 4 and 8 (worked example).

## 4a. Header block

| Field | Your entry |
| --- | --- |
| Product / release | Beacon 1.4.2 — AI-assisted patient triage, Kestrel Health Network. Phases: pilot (Riverside and Hillcrest, 14 Dec 2026); network (nine hospitals, 11 Jan 2027) |
| Checklist version | v1 · 8 Dec 2026 · [your candidate id] |
| Governance structure | Every criterion answers: what is enforced · what evidence exists · where it is logged · who approves |
| Accountable owners by dimension | Business: Marcus Bell · Technical: Neha Sharma · Quality: Victor Osei · Governance: Dr. Helen Mathews · Operational: Kavya Nair |
| Purpose of the 10 Dec Go/No-Go meeting | To confirm, from linked evidence, that the pilot gates have already been passed by their named approvers, and to record the sponsor's decision for 14 December; it is not where gaps are found. |

## 4b. Criteria

Write the three AI-control rows first (Day 3 starts with a 10-minute sprint on them). Each must state: AI-01 Confidence threshold: the metric · the number · where the number came from (which data) · a named owner · what happens below it AI-02 Human-in-the-loop trigger: the condition that sends a case to a person · the named role that receives it · the time limit AI-03 Model drift monitor: what is measured · the baseline · the acceptable band · where the alert goes · who responds · the action on a breach

| ID | Stage · Phase | Dimension | Criterion (a checkable question) | Evidence required | Where logged | Accountable owner (named) | Approver | Status at 8 Dec + basis |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AI-01 | Build · Pilot | Technical (AI control) | Confidence threshold: metric = Beacon confidence on Routine and Self-care messages; number = 0.80; source = ev-118 on 3,000 Kestrel messages; owner = Dr. Farah Siddiqui; below 0.80 = message goes to the nurse queue. Is the configured value 0.80, or any other value re-evaluated on build 1.4.2 and CSO-approved? | triage-config.yaml value matching an evaluation report on the release build; CSO approval of the value | Repository (triage-config.yaml); evaluation report store | Dr. Farah Siddiqui | Dr. Helen Mathews | Not met: config is 0.72, lowered 25 Nov without re-evaluation or CSO approval (E3, E4 26 Nov) |
| AI-02 | Deploy · Pilot | Operational (AI control) | Human-in-the-loop trigger: condition = Emergency or Urgent category, confidence below threshold, any mixed-language or transliterated message, or any patient reply to an automated message; receiver = triage nurse on Priyanka Das's rota; time limit = Urgent within 30 minutes, Emergency limit set by the CSO. Is it met at the 7 to 10 pm peak? | Routing rule in config; staffed night rota showing the urgent peak cleared within 30 minutes; test of each trigger | Nursing rota; routing test log | Priyanka Das | Dr. Helen Mathews | Not met: 2 night nurses need about 75 minutes for the peak; patient replies go to a 48-hour inbox; mixed-language not routed (E4 1 Dec, 3 Dec) |
| AI-03 | Deploy · Pilot | Operational (AI control) | Model drift monitor: measured = under-triage rate from a weekly clinician sample of auto-routed messages, split by language, plus category mix and mean confidence; baseline = ev-118 Kestrel values (2.1% overall, 1.6% English, 6.8% mixed); band = no rise above baseline; alert = paged to Kavya Nair's on-call rota; responder = on-call engineer with Dr. Helen Mathews for the clinical call; action on breach = switch to manual triage. | Dashboard with Kestrel baseline; sampling schedule; paged alert test record | Grafana 'Beacon Drift'; on-call paging log | Kavya Nair | Dr. Helen Mathews | Not met: baseline is CorvidBench, no under-triage measure, no sampling, alerts go to an unpaged chat channel (E5) |
| B-01 | Intent · Pilot | Business | Does intent.md cover portal messages and automated replies, approved by the business owner? | Dated revision of intent.md with approval | Repository (beacon/intent.md) | Marcus Bell | Dr. Anjali Rao | Not met: intent.md covers referral letters only; scope changed in channel on 9 Oct (A5) |
| B-02 | Intent · Pilot | Business | Are the pilot sites agreed? | Executive minutes naming Riverside and Hillcrest | Executive minutes, September | Marcus Bell | Dr. Anjali Rao | Met: executive minutes, September (item 2) |
| B-03 | Plan · Pilot | Business | Are vendor contracts and data-processing agreements signed with India data residency? | CTR-311 and CTR-312 with DPAs | Contract register | Marcus Bell | Grace Liu | Met: CTR-311 (Corvid) and CTR-312 (MedLink), both DPAs with India data residency (item 5) |
| B-04 | Plan · Pilot | Business | Is a pinned Corvid model version contracted and funded, so the 15 Dec alias change cannot reach live patients? | Contract change selecting a pinned version | Contract register (CTR-311) | Marcus Bell | Owen Fletcher | Not met: Kestrel selected the 'latest' alias; pinned versions cost extra (E8 item 27) |
| B-05 | Deploy · Network | Business | Is the network rollout conditional on a network gate decision using pilot benefit and safety results? | Rollout plan v3 with a gate; pilot report | Programme decision log | Marcus Bell | Dr. Anjali Rao | Not met: appendix says the network proceeds automatically after the pilot Go/No-Go (item 28) |
| T-01 | Spec · Pilot | Technical | Is the spec's clinical safety section derived from Kestrel's hazard log, not copied from Corvid's? | spec.md revision referencing the Kestrel hazard log | Repository (beacon/spec.md) | Neha Sharma | Dr. Helen Mathews | Not met: copied from Corvid hazard log; approved by Neha 2 Dec (A5) |
| T-02 | Spec · Pilot | Technical | Has the architecture been re-reviewed for portal messages and automated replies? | Architecture review record dated after 9 Oct | ADR register | Neha Sharma | Rahul Menon | Not met: ADR-009 dated 21 Sep, before the scope change (E8 item 4) |
| T-03 | Plan · Pilot | Technical | Do all 11 features, including automated reply drafting and threshold tuning, have approved plans? | Plan file per feature with approval | Repository (beacon/plans/) | Neha Sharma | Victor Osei | Not met: 9 of 11 plans; the two highest-risk features have none (A5) |
| T-04 | Build · Pilot | Technical | Is the model pinned to a named version in config, with no floating alias? | triage-config.yaml showing a pinned version | Repository (triage-config.yaml) | Neha Sharma | Dr. Helen Mathews | Not met: model is 'corvid-med-latest', moving to 3.3 on 15 Dec (E3, E4 30 Nov) |
| T-05 | Build · Pilot | Technical | Does every decision record include message, category, confidence, rationale, model version, prompt version, threshold, routing outcome, reply text and reviewing nurse? | Sample audit record with all fields | Audit log store | Neha Sharma | Owen Fletcher | Not met: log_fields are message_id, category, confidence only (E3) |
| T-06 | Review · Pilot | Technical | Have the 12 PRs approved by the author of their prompts been independently re-reviewed, with a rule blocking self-approval? | Re-review record; branch protection setting | Repository review log | Neha Sharma | Victor Osei | Not met: 12 PRs approved by Imran, who wrote their prompts (A5) |
| T-07 | Review · Pilot | Technical | Has the penetration test passed, with critical findings fixed and retested? | PT-2026-77 with retest | Security test register | Rahul Menon | Owen Fletcher | Met: 1 critical finding fixed; retest passed 30 Nov; signed R. Menon (item 13) |
| T-08 | Deploy · Pilot | Technical | Is retention set to 8 years for decisions and patient communications? | Configuration export showing 8 years | Repository (triage-config.yaml) | Kavya Nair | Grace Liu | Not met: retention_days: 365 (E3); RP-1 requires 8 years |
| T-09 | Deploy · Pilot | Technical | Has rollback been rehearsed for container, model version and prompt version, and for switching Beacon off so every message goes to nurses? | Dated rehearsal record for each path | Runbook §5; deployment log | Kavya Nair | Priyanka Das | Not met: only container rollback rehearsed, 20 Nov (E6) |
| T-10 | Deploy · Network | Technical | Has technical ownership been handed over from Tobias Grant before his contract ends on 18 Dec? | Signed handover record | Programme decision log | Neha Sharma | Marcus Bell | Not met: no handover; ownership note says 'until handover' (appendix; A3) |
| Q-01 | Build · Pilot | Quality | Has the Kestrel evaluation been re-run on build 1.4.2, with the pinned model and configured threshold, reported by language group? | Evaluation report naming build, model and threshold | Evaluation report store | Victor Osei | Dr. Helen Mathews | Not met: ev-118 ran on build 1.4.0 at 0.80 (E1 footer) |
| Q-02 | Build · Pilot | Quality | Is the regression suite green on the release build? | CI run on build 1.4.2 | CI system | Victor Osei | Neha Sharma | Met: CI #2291 green on 1.4.2, 27 Nov; does not cover the evaluation set (E4 27 Nov) |
| Q-03 | Review · Pilot | Quality | Does the load test show p95 latency within target at 3x pilot volume? | LT-1.4.2 report | Test register | Victor Osei | Kavya Nair | Met: p95 1.8 s at 3x pilot volume, 1 Dec (item 15) |
| Q-04 | Review · Network | Quality | Has load been tested at nine-hospital volume? | Network-volume load test report | Test register | Victor Osei | Kavya Nair | Not met: only pilot volume tested (item 15) |
| Q-05 | Review · Pilot | Quality | Are automated self-care replies at grade 8 or below, in English, Hindi and Marathi? | Readability sample and language test | Evaluation report store | Victor Osei | Dr. Helen Mathews | Not met: grade 11, English only (E1; E8 item 26) |
| Q-06 | Build · Network | Quality | Is the under-triage rate for mixed-language messages no higher than for English messages? | Evaluation by language group | Evaluation report store | Victor Osei | Dr. Helen Mathews | Not met: 6.8% vs 1.6% (E1) |
| G-01 | Review · Pilot | Governance | Is there a Kestrel clinical safety case and hazard log, covering automated replies, mixed-language messages and queue capacity, signed by Kestrel's CSO? | Signed Kestrel safety case and hazard log | Clinical safety register | Dr. Helen Mathews | Dr. Anjali Rao | Not met: only Corvid's hazard log; CSO not asked (E7) |
| G-02 | Review · Pilot | Governance | Is R-17 mitigated, or accepted in writing by the CMO or CSO with a review date? | Risk register entry with signatory and review date | Enterprise risk register | Owen Fletcher | Dr. Helen Mathews | Not met: accepted by Neha Sharma, no review date (E4 5 Dec, 7 Dec) |
| G-03 | Review · Pilot | Governance | Is a DPIA addendum for portal messages approved before any patient message is processed? | Signed DPIA addendum | DPO document store | Grace Liu | Owen Fletcher | Not met: DPIA v1 covers referral letters only (E4 2 Dec) |
| G-04 | Review · Pilot | Governance | Is patient AI-disclosure wording approved, in English, Hindi and Marathi? | Approved wording in each language | Communications approval record | Owen Fletcher | Dr. Helen Mathews | Not met: draft with Legal, English only (E8 item 26) |
| G-05 | Intent · Pilot | Governance | Is each stage gate approved by an independent named approver, not the delivery lead who did the work? | Gate approval record per stage | Programme decision log | Owen Fletcher | Dr. Anjali Rao | Not met: all gates approved by Neha Sharma on 2 Dec (appendix) |
| G-06 | Review · Network | Governance | Is every Corvid model change re-evaluated on Kestrel data and CSO-approved before use? | Change-control procedure and record | Enterprise risk register | Owen Fletcher | Dr. Helen Mathews | Not met: contract gives notice only; supplier calls 3.3 'non-material' (E8 item 27) |
| O-01 | Deploy · Pilot | Operational | Is night-shift staffing enough to clear the urgent peak within 30 minutes? | Rota and capacity calculation | Nursing rota | Priyanka Das | Dr. Anjali Rao | Not met: 2 nurses, about 75 minutes (E4 1 Dec) |
| O-02 | Deploy · Pilot | Operational | Have all pilot-site triage nurses completed the Beacon module? | Learning system completion report | Learning system | Priyanka Das | Dr. Helen Mathews | Not met: 11 of 29 (38%) (E8 item 24) |
| O-03 | Deploy · Pilot | Operational | Does the contact centre have call scripts and a route that sends 'symptoms worse' replies to the nurse queue? | Scripts and routing rule | Contact centre procedures | Sunil Bhat | Priyanka Das | Not met: email link only; replies go to 48-hour inbox (E4 3 Dec; E8 item 25) |
| O-04 | Deploy · Pilot | Operational | Do Beacon clinical alerts page a named on-call rota, not only a chat channel? | Alert routing config and test page | On-call paging log | Kavya Nair | Dr. Helen Mathews | Not met: alerts post to #beacon-alerts, not on any rota (E5) |
| O-05 | Deploy · Pilot | Operational | Is the Go/No-Go pack verified with every row linked to evidence before 10 Dec? | Pack with evidence links | Programme decision log | Neha Sharma | Dr. Anjali Rao | Not met: item 30 calls the meeting 'a formality' (item 30) |
| O-06 | Deploy · Network | Operational | Have pilot results (under-triage sample, queue times, replies to automated messages) been reviewed before 11 Jan? | Pilot operations report | Programme decision log | Kavya Nair | Dr. Anjali Rao | Not met: pilot not yet started |

IDs: B = Business, T = Technical, Q = Quality, G = Governance, O = Operational, AI = the three AI-specific controls (fill in their stage and dimension too). Stages: Intent · Spec · Plan · Build · Review · Deploy. Status: Met / Not met / Unknown, with a one-line basis. Add or remove rows to reach 20 to 35.

# Part 5 · Readiness statement to the sponsor (M4, Day 3)

No more than half a page, addressed to Dr. Anjali Rao. Write it so that it could be forwarded to the regulator unchanged.

| Heading | Your text |
| --- | --- |
| To | Dr. Anjali Rao, Chief Medical Officer |
| What is ready | Beacon 1.4.2 is built and in staging since 18 November. The penetration test passed after a retest, the regression suite is green, and load testing met target at three times pilot volume. Contracts and data-processing agreements are signed, and the pilot sites are agreed. |
| What is not ready | Kestrel has no clinical safety case signed by its own Clinical Safety Officer. The live threshold (0.72) and build were never evaluated, and the model will change automatically on 15 December. Mixed-language messages are under-triaged at 6.8%, and that risk was not accepted by anyone authorised to accept it. The privacy assessment does not cover patient messages. Records are kept for one year, not eight. Self-care replies are too hard to read, English only, and lack approved disclosure. Night nurses cannot meet the 30-minute urgent target, and patients who reply 'worse' wait up to 48 hours. |
| What must happen, at which stage, before 14 December (and before 11 January) | Before 14 December: Build: model pinned and threshold reset to the evaluated 0.80 (Neha Sharma). Review: Kestrel safety case signed (Dr. Helen Mathews); privacy addendum approved (Grace Liu). Deploy: eight-year retention and full decision logging (Kavya Nair); tested switch to manual triage (Kavya Nair); all pilot nurses trained (Priyanka Das). Before 11 January: re-evaluation on the release build by language; mixed-language risk closed or accepted by you or the CSO; compliant replies and disclosure; paged under-triage monitoring with clinician sampling; staffing for the evening peak; handover from Tobias Grant; a network gate decision on pilot evidence. |
| My recommendation, and why | No-go for 14 December as configured. Go on 14 December only if every 'before 14 December' item is evidenced by 11 December, and only with automatic routing and automated replies switched off, so a nurse triages every message and Beacon only advises. Otherwise move the pilot date. Kestrel's own standards require a signed safety case and an approved, evaluated configuration before patient care is affected, and neither exists today. |

# Part 6 · Assumptions

Anything you assumed that the case did not state, for example a tolerance figure you proposed. Leave it empty if you made no assumptions.

| # | What I assumed | Why I needed to assume it |
| --- | --- | --- |
| A1 | Beacon can run in an advisory mode on 14 December, with automatic routing and automated replies switched off (auto_reply_enabled false and no auto-routing), so every message goes to a nurse. | The case shows an auto_reply_enabled flag but does not say routing can be disabled. My conditional go depends on this mode. |
| A2 | Corvid can supply a pinned corvid-med-3.2 version before 15 December, and Marcus Bell will fund it. | The contract says pinned versions exist at extra cost but gives no lead time or price. |
| A3 | Drift band for AI-03: alert when the clinician-sampled under-triage rate for any language group exceeds its ev-118 baseline (2.1% overall, 1.6% English, 6.8% mixed). Final band to be set by Dr. Helen Mathews. | The case gives baselines but no acceptable band, and AI-03 needs one. |
| A4 | The Emergency response limit is set by the CSO. The 30-minute urgent limit comes from v0.9 item 17. | The case states only the urgent target, and AI-02 needs a time limit for each trigger. |
| A5 | Neha Sharma is the Technical Accountable owner, with Tobias Grant Responsible until 18 December. | The case gives no technical owner who stays beyond 18 December other than the delivery lead and the lead engineer, and the lead engineer's self-approvals make him unsuitable as Accountable. |
| A6 | Nine-hospital volume for the network load test is about 4.5 times pilot volume (nine sites against two). | The case gives pilot volume only. A planning figure is needed to scope the network load test. |

# Before you submit

Tick each box only if it is true. Every "no" is a mark you can still recover. The full self-review is in the Lab Kit, Section 10.

| Check | Done? |
| --- | --- |
| Part 1: the cover block is complete | ☐ |
| Part 2: 12 or more findings, covering all five dimensions; the example row is deleted | ☐ |
| Part 3: one named Accountable person for each dimension; no teams, no "TBD" | ☐ |
| Part 4: three separate AI-control rows (AI-01, AI-02, AI-03) with every field | ☐ |
| Part 4: every row has a stage, and all six stages are used | ☐ |
| Part 4: every row names its evidence and where it is logged | ☐ |
| Part 4: statuses match the evidence; "Not met" appears where the evidence says so | ☐ |
| Part 4: the header says the Go/No-Go confirms gates already passed | ☐ |
| Part 5: the readiness statement is written, in half a page or less | ☐ |
| Nothing important is only in an image or only in your head | ☐ |

Submit this file through the submission process your facilitator gives you. You have up to three attempts.